## Sheet1
HREiR Action plan template
Details
| Institution name: | University of Huddersfield | The institutional audience* for this action plan includes:
| Cohort number: | Four | Audience (beneficiaries of the action plan) | Number of | Comments
| Date of submission: | 24.8.2022 | Research staff | 136 | Primarily employed to undertake research only, although this may include limited teaching hours
| Institutional context: | University of Huddersfield Research and Researchers The University of Huddersfield (UoH) was designated university status in 1992. It is a member of UUK and Yorkshire Universities and until November 2018 was a member of the University Alliance (UA). Based within the Leeds City Region, the University is an anchor institution and major employer and in 2019 became a signatory to the UPP Civic University Agreement. Significant economic and demographic challenges exist to drive collaborative R&D with local organisations. The North’s GVA per capita is ~10 to 15% below the UK average (excluding London) with several contributory factors e.g. lack of skilled people, technology gaps and reduced appetite for innovation. The lack of regional private sector R&D investment presents a major challenge for developing collaborative research initiatives with local industry. The University has six academic schools undertaking research in a broad range of disciplines with particular emphasis on STEM, humanities, social sciences, business, art and design (18 Units of Assessment in total). This broad portfolio of activity is also recognised by Huddersfield’s assignment to Cluster E in the KEF exercise. Some research areas are well established and have been submitted to multiple REF and RAE exercises, whilst others such as drama, media, architecture, sports science and psychology this was their first submission. The schools are supported by six central support service directorates and are overseen by the Vice Chancellor’s Office. In total, 2177 FTE staff are employed, of which 45% are academics with 15% of these being at professorial level. All academic staff are expected to be research active and this is reflected in their job roles and workload allocation models. Academic staff are expected to publish research of at least 2* quality by the end of the current University Strategy period (2025), building on the previous strategy (2013-2018) which aimed for all academic staff to be publishing at, or better than, national level. All academic staff, except a very small number of those on practitioner contracts, are returned to HESA categories of Teaching and Research (T&R) or Research Only (RO). Only six academic members of staff are on teaching only contracts. A key element of the University’s strategy is to support academic staff who do not hold a doctorate to become qualified and staff are expected to study for a doctorate either at Huddersfield or elsewhere, before developing into independent active researchers. | Postgraduate researchers | 1280; FTE = 1017 | October 2021 figures
|  |  | Research and teaching staff | 795 | Employed to undertake both teaching and research
|  |  | Teaching-only staff | 6 | Employed only to undertake teaching
|  |  | Technicians | 103 | Technical Services Staff e.g. Technicians, IT infrastructure etc.
|  |  | Clinicians | n/a | n/a
|  |  | Professional support staff | 939 | Professional Services Staff e.g. Administration, Porters, HR Manager etc.
|  |  | Other (please provide numbers and details): | 198 | The staff which fall into the “Other” category include “Campus” staff (e.g. Cleaning staff, Catering staff, Campus Support Officers etc) as well as our KTP Associates which don’t really fit into any other category.
| Obligation | Action | Success measure (SMART) | Deadline | Responsibility | Progress update (to be completed for submission) | Outcome/ result | Action carried over from previous action plan?
Environment and Culture
Institutions must:
ECI1 | Ensure that all relevant staff are aware of the Concordat | A: The University had fairly low levels of awareness around the old Concordat. To improve awareness going forward, we will publicise the revised Concordat to Support the Career Development of Researchers internally and externally. | Awareness score in CEDARS improved by 5%, Question 42 | 2021-03-01 | HoRE & Marketing | A new website area which is more prominent on the University research web pages has been created. https://research.hud.ac.uk/strategy/concordat-career-development/. | Increase in awareness from CEDARS (now Q43.1), 52% in 2020, which breaks down into 24% 'I have some understanding' and '27% 'know this exists but don't know the detail'. Question 43.1a in 2021, 'I have some understanding' currently at 26%, 'I know this exists' at 31%, combined 56% | Complete
|  | B: Run short lunchtime briefing(s) on the Concordat | Awareness score in CEDARS improved by 5%, Question 42 | 2022-03-01 | HoRE & Marketing | Now planned for early 2022, sessions will be online. | Increase in awareness from CEDARS (now Q43.1), 52% in 2020, which breaks down into 24% 'I have some understanding' and '27% 'know this exists but don't know the detail'. Question 43.1a in 2021, 'I have some understanding' currently at 26%, 'I know this exists' at 31%, combined 56%. Not complete - roll into new action | Continue
|  | C: Send a digital copy of the Concordat to all researchers | Awareness score in CEDARS improved by 5%, Question 42 | 2022-03-01 | HoRE & Marketing | Now planned for early 2022 | Increase in awareness from CEDARS (now Q43.1), 52% in 2020, which breaks down into 24% 'I have some understanding' and '27% 'know this exists but don't know the detail'. Question 43.1a in 2021, 'I have some understanding' currently at 26%, 'I know this exists' at 31%, combined 56%. Not complete - roll into new action | Continue
|  | D: Promote the Concordat via URCOG, URG and other committees. | Awareness score in CEDARS improved by 5%, Question 42 | 2021-03-01 | HoRE & Marketing | Promoted because of REF, will continue in 2022. | Change to Concordat promoted through all committees. Increase in awareness from CEDARS (now Q43.1), 52% in 2020, which breaks down into 24% 'I have some understanding' and '27% 'know this exists but don't know the detail'. Question 43.1a in 2021, 'I have some understanding' currently at 26%, 'I know this exists' at 31%, combined 56%. Awareness raising will be continued - roll into new action. | Complete
ECI2 | Ensure that institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers | The University revised their webpages in 2019-20, with all policies being located centrally. However, there is still awareness raising work to be done so we need to embed awareness of policies and procedures relating to research into 'local' School-specific induction processes. Please see here for further details: https://www.hud.ac.uk/policies/ | Feedback on induction in 2022 University of Huddersfield Institutional Survey of Researchers, then again Induction related questions in CEDARS 2023. Aiming for >5% increase in induction related question scores (Q41). | 2023-05-01 | HoRE | Delayed due to Covid 19 and staffing gap in the Researcher Environment team, but in progress. All mapping is complete, following consultations with ADREs, DoGE, Research and Enterprise (now RIKE), People and Organisational Development. Dissemination actions expected to be completed spring 2022, evaluation in May 2022 and June 2023. |  | Continue
ECI3 | Promote good mental health and wellbeing through, for example, the effective management of workloads and people, and effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues | A: Researchers reported lower satisfaction levels around mental health and wellbeing than other staff groups, such as professional services staff, during the 2019 University in QoWL survey. Moving forward the Research Committee will consider the biannual Quality of Working Life Survey and review scores from researchers across the University with the aim of improving satisfaction ratings further. | Satisfaction levels for Research Only in line with or exceeding University Benchmarks for Mixed Portfolio staff for QoWL, Question 54. I often feel excessive levels of stress at work (-ve) | 2023-04-01 | PVC (R&E) & DoHR | Due to start 2022 after QoWL survey. |  | Continue
|  | B: We will monitor awareness and overall use of our new Employee Assistance Programme: VivUp, especially amongst our researcher community. VivUp is an online wellbeing support tool available to all staff. | Ensure our Employee Assistance Programme is embedded into University and local Induction processes, relevant HR procedures and establish appropriate reporting mechanism regarding engagement to URCOG. | 2021-04-01 | HoOH | HR OH purchased VivUp (replacing Silvercloud) mid-December 2020, | Action completed. VivUp is successfully embedded in to our University-wide and local Induction processes and procedures. Reporting mechanisms to URCOG have been established. | Complete
|  | C: Continue roll out of Mental Health First Aid scheme to support staff with their wellbeing and mental health. | Ensure we have sufficient numbers of Mental Health First Aiders. | 2021-12-01 | HoOH | We have qualified Mental Health First Aiders, and continuously review the service to make sure we have sufficient numbers. Where we do not, additional training will offered for new Mental Health First Aiders. | Action completed. | Complete
|  | D: National Wellbeing Charter accreditation achieved in Dec 2018, reapply for accreditation in Dec 2020. | Renewal of National Wellbeing Charter. | 2021-04-01 | HoOH | HR OH team re-applied for accreditation to the National Wellbeing Charter late November 2020. | Action completed. We have been successful with our renewal of National Wellbeing Charter in early 2021. | Complete
ECI4 | Ensure that managers of researchers are effectively trained in relation to equality, diversity and including, wellbeing and mental health | A: The CROS and PIRLS 2019 survey showed EDI scores on career progression/promotion was below the benchmark for the sector. To help address this issue, our aim is for managers to complete Equality, Diversity and Inclusion in the Workplace and Unconscious Bias online training modules. | 75% completion rates monitored through our online learning system, both across the University as a whole, as well as for each School and Service. | 2021-08-01 | HoHR & HP&OD | Roll out for all managers to complete Unconscious Bias online training started in December 2020, whilst planning for Equality, Diversity and Inclusion in the Workplace training will start early 2021. | Action partly complete. At present completion rate for managers stands at 54%, therefore we will continue with this action going forward. | Continue
|  | B: The University will be submitting for Athena Swan Bronze renewal in April 2020. https://research.hud.ac.uk/strategy/athena-swan/ | Successfully achieving Athena Swan Bronze renewal for the University. Further information can be found on https://staff.hud.ac.uk/equality/gender/ | 2020-04-01 | Chair EDIEC | The University submitted for Athena Swan Bronze renewal in April 2020. | Action completed. UoH successfully achieved Athena Swan Bronze renewal in 2020. | Complete
|  | C: Individual Schools Athena Swan submissions. https://research.hud.ac.uk/strategy/athena-swan/athena-swan-in-schools/ | Five out of six Schools submitting and achieving Athena Swan Bronze status. Further information can be found on https://staff.hud.ac.uk/equality/gender/ | Dec-24 Various | Chair EDIEC | As its stands 3 out of our 6 Schools have Athena Swan Bronze or Silver. |  | Continue
|  | D: Roll out training and resources focussing on wellbeing to help raise awareness of the positive steps staff can take to increase the wellbeing for themselves and others. | CEDARS at or above the benchmark for the sector. Q41 in 2020, Q42 in 2021 | 2020-12-01 | HoHR & HP&OD | Roll-out of a number of new wellbeing courses and resources brought forward due to the issues caused by Covid19. We now have a suite of 16 wellbeing courses as well as resources which have been delivered online during the pandemic. | Action completed - New wellbeing courses and resources offered to staff and now Q42.5 is at benchmark for mental health and wellbeing. CEDARS 2021 (was Question 41, Q42 in 2021). 41.4 Your institution actively promotes the importance of good mental health and wellbeing of staff? 65.9% (Benchmark), 66.6% (UoH) 41.5 Your working environment supports your mental health and wellbeing?(Benchmark) 49.6%, 52.2% (UoH) 42.5 You take positive action to maintain your mental health and wellbeing? 78.2% (Benchmark), 78.6% (UoH) | Complete
ECI5 | Ensure that researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity | A: Research integrity training for all relevant staff. | >80% report having undertaken training in Research Integrity via CEDARS, Question 27 | 2022-04-01 | HoRE | In progress. Online Research Integrity training being piloted in some Schools for staff, monitoring via newly established RI Champions network. | In CEDARS 2021, 65% report having completed RI training, a slight decrease from the 2020 figure of 67%. However, there was a slight increase in those interested in training. More information on Research Integrity given below. | Continue
|  | B: Run short lunchtime briefing(s) on the revised Research Integrity Concordat once released. (Combine with action in ECI1) | Awareness score improved by 5% in CEDARS, Question 42. 'I have some understanding of this' 23% in CEDARS 2020, 'I know this exists but I don’t know the detail ' 26% | 2022-03-01 | HoRE in consultation with Marketing | Now planned for early 2022. | Awareness score have improved, but not yet by 5%. In CEDARS 2021, Question 43 (was Q42), 'I have some understanding of this' 27% , 'I know this exists but I don’t know the detail' 29%. | Continue
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and use the outcomes to improve institutional practices | A: Complete focus group work following on from Institutional Survey and report to URCOG with recommendations for the University senior leadership team. | Recommendations agreed by the senior leadership team and implemented. | 2021-06-01 | DoRE & DoHR | A number of focus groups following on from Institutional Survey have taken place and the outcomes were communicated to relevant stakeholders. | Action Complete. | Complete
|  | B: Run CEDARS survey in 2020 | > 30% response rate (from researchers) | 2020-07-01 | HoRE | CEDARS survey ran in July 2020. | Action completed with 29% response rate. The CEDARS survey ran again in 2021 with increased response rate of 32% | Complete
|  | C: Run QoWL survey in 2021 | > 50% response rate | 2021-06-01 | HoHR | Due in 2022. The QoWL is an external survey that is used by a number of institutions. This allows for internal HE sector benchmarking to take place. In 2021 almost all institutions decided to delay their main all staff surveys and instead ofted for more local pulse type surveys and therefore this meant that there was no benchmarking data available. This led to the University taking the decision to delay our all staff survey by a year. |  | Continue
|  | D: URCOG to produce an annual report for University Research Committee, reporting to Senate, including strategic objectives, measures of success, implementation plan and progress. | Report available on public facing website. | 2022-03-01 | URCOG | The URCOG annual report for is in progress, as required through our Concordat commitment. |  | Continue
Funders must:
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Managers of researchers must:
ECM1 | Undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work | Please see ECI4 actions, measures and accountabilities for further details. | [5 empty] | Continue
ECM2 | Ensure that they and their researchers act in accordance with the highest standards of research integrity and professional conduct | A: There is a need to raise awareness of best practices in Research Integrity. We will offer a one-day workshop on research integrity and dealing with research misconduct for key contacts in Schools | Workshop on Research Integrity have been well attended and network of Research Integrity Champions established. | 2020-01-01 | PVC (R&E) | Workshops around Research Integrity well attended and network of Research Integrity Champions established. In January 2020, 18 members of senior academic staff, the Head of HR, the Deputy Director Research and Enterprise and the Head of Researcher Environment participated in a one day training session ‘Ensuring Research Integrity and Effective Misconduct Investigations’ which was delivered by an external consultant. The materials and resources were uploaded to the Researcher Environment module to augment a revised Research Integrity area. Additional materials on the challenges which researching remotely brings were also included following the move to remote working. | The network for the School Research Integrity Champions has been established through a series of online meetings held during the year. This has enabled discussion, sharing of training materials across disciplines and wider communication within and between the Schools. Awareness of the Epigeum Research Integrity packages and the importance of engaging staff in the CEDARS survey has been raised. The Champions were also made aware of the UKRIO and Vitae’s Research Integrity: a landscape study document. A review at School level of the outcome from CEDARS 2020 was carried also out. Detailed report available on Concordat to Support Research Integrity pages: https://research.hud.ac.uk/strategy/concordat-research-integrity/ | Complete
ECM3 | Promote a healthy working environment that supports researchers' wellbeing and mental health, including reporting and addressing incidents of discrimination, bullying and harassment, and poor research integrity | A: Increase awareness of the options available to line managers regarding the promotion of a healthy work environment. Our solution is the HR Managers Induction. All new line managers go through a series of HR policies and procedures (1:1) with our HR managers. | Role induction score increased by 5% in CEDARS, Question 19.3a, 68% (2020) for Very Useful/Useful local induction to role. | 2021-04-01 | HoHR | The HR Managers Induction has been designed and is being offered to all new line managers on a 1:1 basis. | Action Complete. Score on CEDARS 2021 at very useful/useful for Q20.3a on 'induction local to your current role'. Action complete. However, we have not yet seen whether the HR managers induction has had an impact on the measure for this action therefore we have marked this as continuing. | Complete
|  | B: We want to increase support for mental health issues. We will continue to develop the network of Mental Health First Aiders through training, peer support for MH First Aiders themselves, and the incident reporting system. | Ensure we have at least one qualified Mental Health First Aiders working in every School. | 2021-04-01 | HoOH | We have at least one qualified Mental Health First Aiders in every School, and continuously review the service to make sure we have representation in every School and Service. Where we do not, additional training will offered for new Mental Health First Aiders. | Action complete. | Complete
ECM4 | Consider fully, in accordance with statutory rights and institutional policies, flexible working requests and other appropriate arrangements to support researchers | Flexible working policies are in place and awareness raising addressed in previous Action Plan - No additional initiatives planned at this time. | [5 empty] | N/A
ECM5 | Engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | A: In the Institutional Survey, nearly 60% of researchers reported feeling mostly or completely that they belonged within the University Community. Our Schools to review existing provision of seminar and reading groups and share best practices, via URCOG | >70% of researchers report feeling mostly or completely that they belong within the University Community. UoH Survey of Researchers 2019 stood at 55% | 2022-01-01 | ADRES | Target of 70% in cross institutional survey, runs again in 2022. There are a number of areas of good practice. For example, in the School of Education & Professional Development all staff ECRs are supported and mentored through our Supported Writing Programme. They are offered places on fully-funded writing retreats and research conferences, and their work is presented at both HudCRES seminars and at annual School Research Conference (where our School research strategy is also discussed). Projects and publications by ECRs are also featured in regularly HudCRES research centre newsletter. | Impact will be measured in the University of Huddersfield Survey of Researchers in May/June 2022. | Continue
|  | B: Gauge interest for a researcher focussed one day event to be held within the period of the action plan. | >70% of researchers report feeling mostly or completely that they belong within the University Community. UoH Survey of Researchers 2019 stood at 55% | 2022-12-01 | DoRE & HoRE | Feedback from CEDARS and representatives on URCOG suggests there is appetite for a university wide research event. Change in DoRE in January 2022 may impact plans. |  | Continue
Researchers must:
ECR1 | Actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students | A: Our supervisor training includes updates on EDI: approximately 40 % of those eligible to supervise have undergone training in the last three years. Continue roll out of Supervisor Training. | 80% of eligible supervisors to have undertaken supervisor training in the last three years. | 2022-06-01 | DoGS & DoGEs | Change in DoGS and delayed due to Covid 19, but in progress. Regulations and best practice mean we have to maintain this target. Training pivoted to online, including compulsory quiz. Seven iterations of training planned for 2021-2022. Supervisory capacity to be added to PDPR. |  | Continue
|  | B: Mandatory Internal Examiner training has been introduced, but there is a backlog in training leading to ad hoc sessions. To solve this issue we will continue roll out of Internal Examiner training | Internal Examiner training supply meets demand and ad hoc sessions are no longer required. | 2021-12-01 | DoGS | The supply of examiners is meeting demand and ad hoc training sessions are now rarely required. | Action complete | Complete
|  | C: The University Press publishes an undergraduate and taught postgraduate research journal Fields. To raise the profile of research only staff, a special issue is planned to highlight student collaboration with research only staff. | Special issue published | 2022-06-01 | University Press & DoRE | In progress. Proposal to have a researcher only person featured each time instead - will have greater impact. | Not being taken forward. | N/A
|  | D: A special issue of the University’s Discover magazine to highlight the impact of research undertaken by research only staff | Special issue published | 2022-06-01 | Marketing & DoRE | In progress - it is proposed to have a researcher only person featured in the future which will have greater impact. Current issue is in the planning stages, researchers to profile have been identified. |  | Continue
ECR2 | Ensure they act in accordance with employer and funder policies related to research integrity, and equality, diversity and inclusion | Research integrity and EDI addressed above. Please see ECI5-A, ECR1 actions, measures and accountabilities for further details. | [5 empty] | Continue
ECR3 | Take positive action towards maintaining their wellbeing and mental health | A: Wellbeing has been identified as an area of potential concern for researchers. People and Organisational Development will develop a theme on Wellbeing to include several new and impactful courses and resources to support researchers’ positive wellbeing and mental health. | CEDARS score improved by 5% for mental health/ wellbeing, Questions 40.4 & 40.5. Wellbeing Theme launched and regular Wellbeing session delivered. | 2021-05-01 | HP&OD | Roll-out of a number of new wellbeing courses and resources brought forward due to the issues caused by Covid19. We now have a suite of 16 wellbeing courses as well as resources which have been delivered online during the pandemic. P&OD will review take up by our research only and mixed portfolio staff communities in 2021, and plan to increase engagement if needed. | Action completed - New wellbeing courses and resources offered to staff and there has been an increase >5% points for both questions 40.4 & 40 (now Q41.4 and 41.5). 56% to 67% for 'your institution actively promotes the importance of good mental health and wellbeing of staff' and 42% to 52% for 'your working environment supports your mental health and wellbeing'. | Complete
|  | B: Staff Wellbeing and Benefits Fair held annually. | Improved score in QoWL scores in May 2023 (when compared to our 2019 QoWL survey) for Mental Health and Wellbeing amongst our research only and mixed portfolio staff communities. | 2023-05-01 | HoHR | HR OH hold Annual Staff Wellbeing and Benefits Fair and will review take up by our research only and mixed portfolio staff communities in 2021, and plan to increase engagement of researchers. |  | Continue
|  | C: Mental Health awareness initiatives (learning lunches with different themes) run by OH for all staff to attend. | Improved score in QoWL scores in May 2023 (when compared to our 2019 QoWL survey) for Mental Health and Wellbeing amongst our research only and mixed portfolio staff communities. | 2023-05-01 | HoOH | HR OH run a number of Mental Health awareness initiatives (learning lunches with different themes) and will review take up by our research only and mixed portfolio staff communities in 2022, and plan to increase engagement of researchers. |  | Continue
ECR4 | Use available mechanisms to report staff who fail to meet the expected standards of behaviour, particularly in relation to discrimination, harassment, bullying, and research misconduct | A: ‘Report and Support’ initiatives were introduced in 2019. We will include the university’s recently introduced ‘Report and Support’ in researcher induction and Supervisor training. https://reportandsupport.hud.ac.uk/Pages/Default.aspx | Monitor via CEDARS, target of 5% increase, Question 37 | 2021-05-01 | HoRE | Report and support was included in supervisor training from April/May 21 (not promoted via induction). 38.1 I am familiar with my institution’s mechanisms to report bullying or harassment 62.8% (Benchmark) 68.4% (UoH) 38.2 I would feel comfortable reporting an incident of bullying or harassment 64.0% (Benchmark) 70.8% (UoH) 38.3 I trust that my institution will investigate any reported incident of bullying and harassment fairly 60.9% (Benchmark) 71.7% (UoH) 38.4 I trust that my institution would take action if appropriate after such an investigation 56.7% (Benchmark) 68.3% (UoH) | Awareness, reporting, investigating and trust scores have all improved significantly and are above benchmark for the sector. 38.1 I am familiar with my institution’s mechanisms to report bullying or harassment 62.8% (Benchmark) 68.4% (UoH) 38.2 I would feel comfortable reporting an incident of bullying or harassment 64.0% (Benchmark) 70.8% (UoH) 38.3 I trust that my institution will investigate any reported incident of bullying and harassment fairly 60.9% (Benchmark) 71.7% (UoH) 38.4 I trust that my institution would take action if appropriate after such an investigation 56.7% (Benchmark) 68.3% (UoH) | Complete
|  | B: Existing mechanisms are in place for reporting research misconduct. We will also Include Research Integrity in researcher Induction framework. See https://research.hud.ac.uk/strategy/concordat-research-integrity/ | Monitor via CEDARS, target of 5% increase, Question 38 | 2021-03-01 | ADRES (was UREIC) & HoRE | Whole University approach delayed due to Covid 19. Some progress made on a School by School basis. Research integrity within SEPD is monitored by our SREIC. All academic staff confirm at annual appraisal that their approved research approaches remain unaltered, and that training is up to date. The University are signatories to the Concordat to Support Research Integrity which has its own action plans and reporting, see https://research.hud.ac.uk/strategy/concordat-research-integrity/ | Research integrity scores in CEDARS have all improved and are significantly above benchmark for the sector. 39.1 I am familiar with my institution’s mechanisms to report incidents of misconduct 58.2% (Benchmark) 75.5% (UoH) 39.2 I would feel comfortable reporting any incidents of research misconduct 67.5% (Benchmark) 80.1% (UoH) 39.3 I trust my institution to investigate any reported incidents of research misconduct fairly 67.0% (Benchmark) 81.4% (UoH) 39.4 I trust that my institution would take action if appropriate after such an investigation 64.6% (Benchmark) 78.6% (UoH) | Continue
ECR5 | Consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | A: Institutional Survey and focus groups have provided rich data on research environment and culture. We will continue to Run Institutional Survey and focus groups. Institutional Survey to include a question which enables reporting from: PGRs; staff doing a PhD; research only staff; and mixed portfolio staff. | Maintain or improve response rate for Institutional Survey for research only and mixed portfolio staff. | 2022-08-01 | DoRE | Due to start March 2022 |  | Continue
Employment
Institutions must:
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices | All managers that are involved in Recruitment and Selection activities including drafting job adverts, shortlisting and interviewing are required to undertake online Recruitment and Selection training and Unconscious Bias training. No additional actions planned at this time. | [5 empty] | N/A
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position | A: Induction scores in CROS 2019 show improvement, but not yet at 2019 target of 80%. We will make further improvements to induction processes, including targeted support for those in research only or mixed portfolio roles. P&OD to make improvements to the University-wide Induction, the HoRE to researcher specific local induction requirements. | CEDARS (2023) scores for induction improve by 5%, Question 19. In 2020, institutional induction was at 61%; in 2021 65% (now Q20). | 2021-12-01 | HP&OD & HoRE | P&OD have made significant improvements to the overall University-wide Induction process. This includes a feedback and monitoring loop (for each School and Service) to help share good practices, and make improvements to how staff are being inducted; new mandatory online modules - such as sexual harassment awareness; virtual sessions – such as the virtual campus tour (especially useful during the pandemic); best practice induction checklists and manager guidelines to help new staff settle into their role. In January we are also due to launch a new staff welcome video new starters. https://staff.hud.ac.uk/hr/staffdevelopment/induction-and-settling-in/ The HoRE is working on the researcher-specific elements of the induction process. | Action partly complete therefore marked as continue. Improvement at institutional level. Scores for institutional induction improved from 61% in 2020, to 65% in 2021, and departmental induction scores also improved (>5%) as did the score for local to current role. | Continue
|  | B: The process of developing the researcher induction framework raised some awareness of current provision but has also identified gaps. We will disseminate researcher induction framework following February 2020 focus group and subsequent revisions. | CEDARS (2023) scores for induction improve by 5%, Question 19. In 2020, institutional induction was at 61%; in 2021 65% (now Q20). | 2022-03-01 | HoRE | Delayed due to Covid 19 and staffing gap in Researcher Environment Team but in progress. Consultation with ADRES, P&OD, members of RIKE completed. Induction activities and requirements mapped against 'required', 'recommended' and 'desired' and by 'new to institution' and new to research/independent research, or research leadership. Dissemination remains to be completed. | Action partly complete therefore marked as continue. Improvement at institutional level. Scores for institutional induction improved from 61% in 2020, to 65% in 2021, and departmental induction scores also improved (>5%) as did the score for 'local to current role'. | Continue
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances | A: The institutional survey indicates that there is a lack of transparency around pathways to promotion. Strategy map theme ‘People first’ includes aim to recognise contribution and provide a fair and motivational framework to ensure colleagues’ engagement for continuous improvement. Work is being undertaken on identifying the expectations of our Researchers at the various stages of their career and this will help to define clearer pathways for progression and promotion opportunities. | Monitor through CEDARS with a target of 5% increase, Question 16. 2020, 16.a was at 55%; in 2021 at 58% (now Q17.1a) | 2024-04-01 | HoHR | Some initial work has started by reviewing the job descriptions for the different resercah roles. HR have worked with one of the Academic Schools to implement an internal promotions and career development process. | All sections of Q17 around promotion, career progression, have increased, some by nearly 5%. Only redundancy processes have decreased scores, perhaps due to major restructure (including the merger of two Schools). | Continue
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent | A: The principles of great management & leadership are integral to of our success in supporting the challenges faced by our research community and agenda. All our managers to achieve Chartered Manager status or registered on management and leadership programmes in order to become Chartered Managers. This will be achieved through a series of CMI-accredited management and leadership programmes. | All (100%) of our managers having achieved Chartered Manager status or registered on management and leadership programmes in order to become Chartered Managers. Completion rates for the percentage of people managers who manage researchers, both across the University as a whole, as well as from each School and Service, to be included in the URCOG Annual Report. | 2022-06-01 | HP&OD | All our managers (500+) have achieved Chartered Manager status or are registered on management and leadership programmes to become Chartered Managers. | Action complete. All our managers as having Chartered Manager status or registered on management and leadership programmes to become Chartered Managers. https://staff.hud.ac.uk/hr/staffdevelopment/management-matters/ | Complete
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation | A: Implementation of the workload allocation model was an area of concern for researchers in the Institutional Survey and follow up focus groups. HR to review how the workload allocation model is currently used especially relating to research, and to make recommendations to senior management and Schools. | Recommendations submitted to University senior leadership team for consideration | 2021-06-01 | DoHR | University wide Workload Allocation Model working group established with representation from all School's. This group considers the different elements of the role and how this can be fairly and consistently acocunted for in a model. The Group meets monthly and will continue to do so. | Action complete. Recommendations submitted to University senior leadership team for consideration | Complete
|  | B: Institutional Survey and focus groups indicated mixed use of sabbaticals. We will review the University’s approach to sabbaticals for research staff and to determine best practice approaches across the Institution. | Recommendations submitted to University senior leadership team for consideration. | 2022-12-01 | DoHR | Due to start in early 2022. |  | Continue
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress | A: Flexible working is important to staff and supported by the Institution as it allows for a better work-life balance and mental wellbeing. We will Continue to offer several flexible working arrangements and ensure these are available to all staff including our research community. | Monitor through CEDARS with a target of 5% increase, Question 13.6 which was at 63% in 2020, & 26.10, which was at 81% in 2020. | 2022-04-01 | HoHR | Continue to offer several flexible working arrangements and ensure these are available to all staff including our research community. | Action complete. Now Q14.6a, which has shown improvement around the extent to which participants agree that the institution treats them fairly for requests for flexible working: 81% (Benchmark) 74% (UoH). Decrease slightly on Q25.10, from to 81% to 77%, but still above the benchmark (75%). Target met >5% for flexibility, but down for managing it, which perhaps reflects the difficulty of managing flexible working during Covid. | Complete
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making | A: Representation of early career researchers in university committees is not well documented. We will conduct review of representation of early career researchers across all university research and School research committees and disseminate findings with a view to sharing best practices. | Raised awareness of opportunities for researcher voice (especially those in the early stage of their career) | 2021-12-01 | URCOG and Chair URCOG | In progress, continue into 2022, URCOG and Graduate Board now have ECR representation. | Action partly complete therefore marked as continue. ECRs representatives have now been included in the membership of Graduate Board, and Annual PGR Lifecycle. | Continue
|  | B: Review of Terms of Reference for Graduate Board, University Research Committee and URCOG to identify roles where early career researchers can have meaningful input, and ensure that those on research only and mixed portfolio contracts are represented in appropriate fora. | Researchers at all stages of their career are represented in institutional research committees. | 2022-04-01 | PVC (R&E) & DoHR | Review of representation is currently in progress. |  | Continue
|  | C: Report on outcome of Students’ Union PGR representation project | Raised awareness of opportunities for researcher voice | 2021-06-01 | DoGS (in collaboration with the Students Union) | Report considered at Graduate Board, and further work is in progress. | Action complete. | Complete
Funders must:
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Managers of researchers must:
EM1 | Undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care | All managers that are involved in Recruitment and Selection activities including drafting job adverts, shortlisting and interviewing are required to undertake online Recruitment and Selection training and Unconscious Bias training. No additional actions planned at this time. See EI4-A and ECR1-A | [5 empty] | N/A
EM2 | Familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding | A: Grant funding requirements are monitored by the Pre and Post-Award teams in Research & Enterprise. Research and Enterprise will run workshops and offer 1:1 support on funding opportunities, bid writing and grant reporting. | Increased bid submission and success rates, monitored by RIKE (was R&E) and Schools) and inline with KPIs in the University strategy (negotiated by School). | 2024-05-01 | DoRE & ADREs | In progress, action continued from previous plan. Recent changes within the Service may impact KPIs in the short term. |  | Continue
EM3 | Commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers | Please see ECI4 actions, measures and accountabilities for further details. | [5 empty] | Continue
EM4 | Actively engage in regular constructive performance management with their researchers | A: We want to create an environment in which our researchers strive to continuously improve themselves and their performance. A new Academic Appraisal process and form will further help ensure all managers have regular performance and development conversations with their researchers and set clear development plans and targets. | Monitor through CEDARS with a target of 5% increase, Question 20a 'How useful did you find your staff review/appraisal?' was at 59% in 2020, & 26.4 around confidence levels in managing the appraisal/review processes effectively was at 90%. | 2021-05-01 | HP&OD & HoHR | A new Academic Appraisal process has been rolled out, and will be reviewed in late 2021/ early 2022. | Action complete, but not met CEDARs target. Appraisal uptake was down 2% at 84% for 2021 (now Q21), with usefulness down 1% to 58%. For Q26, 11% responded 'NA' reflecting the challenges of managing during the pandemic which meant that there was an impact on the number of appraisals which participants report having taken place. | Complete
EM5 | Engage with opportunities to contribute to relevant policy development within their institution | A: Researcher representation is not well documented. We will review membership of relevant University and School Research Committees to ensure appropriate representation across the researcher life cycle | Opportunities included in induction framework and disseminated to managers. | 2022-06-01 | URCOG | In progress, not complete. Will be shared via POD website and disseminated via URCOG to share locally. |  | Continue
|  | B: Explore the possibility of establishing research related networks around particular areas of relevance for researchers | Monitor through CEDARS with a target of 5% increase, Question 41.4, now Q 42.4 and score for the 'extent to which you feel included in your immediate research environment/group?' is at 73% (2021). | 2024-05-01 | PVC R&E, ADREs & DoGS | In progress. Networks not yet established. |  | Continue
|  | C: Run focus groups following the Institutional Survey planned for 2022 | Monitor through CEDARS with a target of 5% increase, Question 15.7, 'To what extent does your institution value the contributions that you make to institutional policy and decision-making?' stood at 26% in 2020. | 2022-05-01 | DoRE & DoHR | Due to start after the Institutional Survey. Focus groups carried out and fed into policy making. | The CEDARS score for Question 16.7 (was Q15.7), 'To what extent does your institution value the contributions that you make to institutional policy and decision-making?' has improved from 26% in 2020 to 48% in 2021. Also potentially impacted by the WAM working group interventions (see elsewhere). | Continue
|  | D: Delivery of Public Impact & Engagement events. | Monitor through CEDARS with a target of 5% increase, Question 33.4. In 2020, 35% reported they had carried out public engagement activity, 48% reported they would like to. | 2022-05-01 | Interim DoRE (Enterprise) | A working group/task and finish group to be formed to start the training side off. A meeting will be scheduled in December 2021/January 2022. Budget is available for some external training and, based on the Watermark Action Plan, it is suggested that an external could be brought in for some work with Senior Leaders before tackling the rest. A meeting with the new PE Champions will take place in December to discuss the new peer support network. | 2021 CEDARS, score for 'have done' dropped to 24%, 'would like to do' increased to 56%. The decrease in activity is likely to be due to the reduction in activities which were possible given government restrictions. | Continue
|  | D: Delivery of Public Impact & Engagement events. | Monitor through CEDARS 2023 with a target of 5% increase, Question 33.4. In 2020, 35% reported they had carried out public engagement activity, 48% reported they would like to. | 2023-05-01 | Interim DoRE (Enterprise) |  |  | Continue
Researchers must:
ER1 | Ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder | Reporting to line managers and through PDPRs (Appraisal). No additional actions planned at this time. | [5 empty] | N/A
ER2 | Understand their reporting obligations and responsibilities | Reporting to line managers and through PDPRs (Appraisal). No additional actions planned at this time. | [5 empty] | N/A
ER3 | Positively engage with performance management discussions and reviews with their managers | Reporting to line managers and through PDPRs (Appraisal). No additional actions planned at this time. | [5 empty] | N/A
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community | Please see EI2-B actions, measures and accountabilities for further details. | [5 empty] | N/A
Professional and Career Development
Institutions must:
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors | A: A gap analysis to identify current provision for at the induction stage for researchers has been completed, for those new to the role, new to the institution, or both. The resulting framework will inform researcher development initiatives for existing staff. We will review researcher development opportunities for staff, identify gaps, and make recommendations. | Recommendations disseminated through URCOG | 2022-03-01 | HoRE | Delayed due to the pivot to online for delivery of all programmes and staffing gaps in the Researcher Environment team, but in progress |  | Continue
|  | B: We want to embed the expectations for 10 days of professional development for relevant staff. We will brief R&E Pre and Post Award teams and academic staff on revised Concordat obligation around professional development | Resource for Professional Development included in new bids | 2020-12-01 | DoRE | Teams briefed. | Action complete. | Complete
|  | C: Develop a system for tracking CPD days, including evidence of uptake. | All research staff to have an annual PDPR (appraisal) and action plan disseminated to senior staff | 2022-04-01 | HP&OD & HoHR | Tracking to be included in a new online PDPR (appraisal) system to be rolled out in April 2022. |  | Continue
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers | A: P&OD to provide a wide variety of training, both face-to-face and online, courses and resources. P&OD will review take up by our research only and mixed portfolio staff communities in 2021, and plan to increase engagement if needed. | Monitor through CEDARS with a target of 5% increase, Question 30 & 30.a | 2021-02-01 | HP&OD | A new Performance Enhancement Theme has improved the ability of reviewers (Appraisers) to have quality conversations (including development conversations) with researchers. https://staff.hud.ac.uk/hr/staffdevelopment/pft/ | Action complete. Partly met target for CEDARS (now Q31 and 31.a). We have increased, but not met target 5% improvement. Note that many academic staff were not able to have appraisals during Covid. | Continue
|  | B: We must monitor progress through improved feedback and evaluation of P&OD offer. To do so we will gather metrics about satisfaction levels, change stories, impact and engagement with learning from our researchers. This will be included in the URCOG Annual Report. | Report disseminated to relevant committees, including URCOG | 2022-03-01 | HP&OD & HoRE | Reporting on engagement with training, career development opportunities and engagement with PDPRs (Appraisals) currently being undertaken ready to be included in the URCOG Annual Report. |  | Continue
|  | C: Develop a system for ensuring all staff have career development conversations with their line managers. | All research staff to have an annual PDPR (appraisal) | 2022-04-01 | HP&OD | Tracking to be included in a new online PDPR (appraisal) system to be rolled out in April 2022. |  | Continue
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers | A: We need to continue to develop initiatives to support researchers in their careers. To do so we will run Career Planning Workshops. | Careers service now represented at URCOG and uptake on careers planning workshops by research only and mixed portfolio staff reported to URCOG. | 2021-12-01 | HoCS | Careers service now represented at URCOG to help with monitoring engagement by our researcher only and mixed portfolio staff groups. | Action complete. All academics have access to 24 hour careers and employability support which cover the following topics; Enhancing CVs; Interview support; Assessment Centres and Psychometric tests; Networking skills; Creating your LinkedIn profile; Career planning; Working globally; Career change; Access to MyCareerPlus, an online portal with over 200 resources. Information and advice on career development is available from experts on a range of topics both in person, through webinars and a bitesize video series. Topics cover the full employment cycle from applications through to negotiating contracts - Virtual assessments include psychometrics, assessment centre tests and an automated CV checker. | Complete
|  | B: To ensure our academics are continually developed we host a Careers and Employability conference annually to which all research staff are invited. | Monitor through CEDARS with a target of 5% increase, Question 29 | 2021-12-01 | HoCS | Planning scheduled for the 2021 Careers and Employability Conference but did not run due to Covid, going forward careers service help with monitoring engagement by our researcher only and mixed portfolio staff groups. |  | Continue
|  | C: Our research and mixed portfolio staff are supported by the Careers and Employability service (see above), but awareness of the offer may be limited. The service will be actively promoted to research only staff who will be able to book a 1:1 career discussion, or careers coaching session with a fully trained careers consultant. These appointments are available both virtually and in person. | Uptake of the careers service opportunities by research only and mixed portfolio staff reported to URCOG. | 2021-06-01 | HoCS | Planning scheduled in 2021 to promote the Careers service to our research only and mixed portfolio staff, with a special focus on the needs of those on fixed-term contracts | Action complete in Jun-21, and then annually. | Complete
|  | D: Relatively new researchers on research only contracts lack opportunities for peer support across the institution. Pilot intervention to build a self-sufficient network of researchers who may understand and support each other’s professional development with the aim of creating a legacy of individuals to lead on modelling good practice in relation to ongoing professional development across the University. To target research only staff in the first instance. | Initiative to include an impact report and recommendations for sustainability. | 2022-06-01 | DoRE & HoRE | Alternative approach using workshops and coaching to take place in Spring 2022 targeting research only staff in the first instance. |  | Continue
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills | A: Promoting a research intensive culture is a key priority. We will consider ways to improve linking of researchers to UoH Areas of Strategic Research and Importance and associated institutions and centres | Increase in collaborative projects submitted for funding and / or co-supervision of PhDs | 2021-12-01 | PVC R&E & ADREs | There has been an internal URF call, developing collaborative opportunities: 8 collaborative multidisciplinary proposals were submitted for funding from the University Research Fund in summer 2021 for Areas of Strategic Research Importance. | Action complete. 16 projects were awarded funding with an average value of £147,000 for the next 3 years in ASRIs of wellbeing, data science, sustainable environment, health, creativity, security, materials, productivity and engineering systems. | Complete
|  | B: Promote the benefits of co-supervision for researchers’ careers in all levels of supervisor training | Increase in co-supervision of PhDs by early career researchers | 2022-10-01 | HoRE & DoGS | In progress, ongoing, and tied in with supervisor training targets for initial training and updates (80% of those eligible to supervise trained by July 22). |  | Continue
|  | C: R&E run sandpits for researchers across the University to bid for pump-priming projects addressing Global Challenges | Increase in collaborative projects submitted for funding | 2021-12-01 | R&E | Global challenges sandpits were run in 2019. Two projects were successful and one has now been funded centrally. | Action Complete - The funding structure has now changed, so there are no plans to run these in this format in the future.` | Complete
|  | D: There are a high number of staff undertaking PhDs, this was a particular area of concern in both the Institutional and CROS surveys. We will review current support provision for staff postgraduate researchers and make recommendations. | Include new institutional question in CEDARS on Staff PhDs and report to Graduate Board and URCOG | 2021-05-01 | HoRE | Staff PGR feedback from PRES and CEDARS has been included in reporting. | Staff PGR access to training is under review and stakeholders in Schools are aware of the challenges. | Complete
|  | E: Establishment of a network or networks of research mentors/ future research leaders, exploring both internal and inter-institutional options. | Network established | 2022-06-01 | HoRE | Pilot inter-institutional mentoring network established, first cohort completes Feb 2022, Mid-Career Mentoring Network: https://mcrmentoringprogrammenw.wordpress.com/ | Evaluation of pilot planned for Spring 2022. | Continue
|  | F: Evaluate the strategy already piloted of requiring early career researchers to be part of supervisory teams on internal bids for EPSRC funded PhD scholarships; and make recommendations for widening the scope to other funding. | Increase in co-supervision of PhDs by early career researchers and included in URCOG Annual Report | 2022-12-01 | DoRE | Insufficient completions to date to assess ECRs as co-supervisors, suggest revisit in Dec-22 |  | Continue
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this | A: Offer secondments, partnership working and training through initiatives such as the Grow MedTech consortium and similar projects to industry, the third sector, the NHS, and government. | Achieve university internal targets for links. | 2024-06-01 | DoRE | In progress - New opportunities will be available through Impact Accelorator Account. |  | Continue
|  | B: Offer workshops in the commercialisation of research. | Achieve university internal targets for links. | 2024-06-01 | DoRE | In progress - Significant ramping up of support for pre-commercialisation accelerator programmes – most notably Innovation to Commercialisation of University Research (ICure) and Lean Launch Pad with 9 projects awarded. |  | Continue
|  | C: Support researcher participation in the ‘Proof of Concept’ competition. | Achieve university internal targets for links. | 2024-06-01 | DoRE | In progress - all funding in 20/21 with new rounds from 21/22 Higher Education Innovation Fund (HEIF) funds. |  | Continue
|  | D: Offer training and support on Intellectual Property. | Achieve university internal targets for links. | 2024-06-01 | DoRE | In progress - also major usage and promotion of UK Intellectual Property Office on line training provision to PGRs and researchers. |  | Continue
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities, and researcher career development reviews | A: Responsibility for recording development is devolved to Schools. Once the new academic appraisal scheme is fully embedded, Schools to monitor engagement of researchers with continuing professional development. | Report to URCOG and feed into annual report | 2022-10-01 | ADRES | In progress. | No | Continue
Funders must:
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning | N/A | N/A | N/A | N/A | N/A | N/A | No
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes | N/A | N/A | N/A | N/A | N/A | N/A | No
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit | N/A | N/A | N/A | N/A | N/A | N/A | No
Managers of researchers must:
PCDM1 | Engage in regular career development discussions with their researchers, including holding a career development review at least annually | A: A new Academic Appraisal process and form are being developed which will further help ensure all research active staff have a clear development plan and targets. Once process and form are approved, undertake a dissemination exercise to ensure all researchers and managers of researchers are aware of the new system. | Research only and mixed portfolio staff to have an annual Appraisal (PDPR). The PDPR applies to all permanent and fixed term staff across our University. | 2021-06-01 | HoHR | A new process and form has been approved and disseminated. | Action complete. We will be reviewing its success in mid-2021 and make any improvements if needed, with a specific focus on both our research only and mixed portfolio staff | Complete
PCDM2 | Support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments | Mentoring for researchers is highlighted as a priority from the Institutional Survey. We will disseminate best practice around research mentoring. | Monitoring through Institutional Survey questions around mentoring and focus groups. | 2024-06-01 | ADREs, HoRE & HP&OD | A review of both Coaching & Mentoring (C&M) has been completed, and a new strategy for C&M has been developed and approved through P&OD. Mentoring of researchers is already working well in some Schools, but we are planning a more joined up, University-wide approach. The HoRE is working with the ADREs and other key stakeholders to map existing mentoring initiatives specific to researchers and encourage the sharing of best practices. Questions on mentoring in the 2022 UoH Survey will provide us with baseline data. |  | Continue
PCDM3 | Allocate a minimum of 10 days pro rata, per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development | Please see PCDI1 A - C actions, measures and accountabilities for further details. | [5 empty] | Continue
PCDM4 | Identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours | Please see EI4-A actions, measures and accountabilities for further details. | [5 empty] | Continue
PCDM5 | Engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development | Please see PCDI1 A - C actions, measures and accountabilities for further details. | [5 empty] | Continue
Researchers must:
PCDR1 | Take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year | A: Embed dedicated training for early career researchers to enable transition to/from their role. | Training embedded and outcomes included in annual narrative report to URCOG. | 2021-06-01 | HoRE | Been offered but low uptake. "What can I do with a doctorate?" Reconsider offering as part of wider training review for researchers. | Very successful for those who have taken part. "WCIDWD programme was exactly what I needed to encourage me to deliberately start planning my career now. It was an opportunity to envision my future while designing achievable steps to moving forwards." | Complete
|  | B: Review training offer to researchers. | Report and recommendations shared at URCOG. | 2021-03-01 | HoRE | Delayed due to Covid 19 and gaps in staffing in the Researcher Environment team. Mapping of training offered centrally is complete, reporting is still outstanding. |  | Continue
PCDR2 | Explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments | Please see PCDI1 A - D actions, measures and accountabilities for further details. | [5 empty] | Continue
PCDR3 | Maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications | Please see PCDI4; EI4; EI5 ECR1 actions, measures and accountabilities for further details. | [5 empty] | Continue
PCDR4 | Positively engage in career development reviews with their managers | Please see PCDI5 A - D actions, measures and accountabilities for further details. | [5 empty] | Continue
PCDR5 | Seek out, and engage with, opportunities to develop their research identity and broader leadership skills | There must be opportunities for research only and mixed portfolio staff to develop their leadership skills, not just those staff in managerial roles. A new Developing Great Leaders Strategy has been developed and approved and has led to the development of a series of CMI accredited management and leadership programme. | All (100%) of our managers having achieved Chartered Manager status or registered on management and leadership programmes in order to become Chartered Managers. | 2022-05-01 | HP&OD | CMI L7 and CMI L5 accredited programmes widely rolled out amongst our academic community. All (100%) of our managers having achieved Chartered Manager status or registered on management and leadership programmes in order to become Chartered Managers. https://staff.hud.ac.uk/hr/staffdevelopment/management-matters/ | Action complete. | Complete
PCDR6 | Consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation | All P&OD and PGR training is mapped against the Researcher Development Framework. However, awareness of the tool for planning professional development could be improved amongst researchers. We will create induction and training frameworks to be aligned with the Researcher Development Framework and development opportunities. | Frameworks available on University website and information about them disseminated to researchers. | 2021-12-01 | HoRE | Delayed due to Covid 19 and staffing gap in the Researcher Environment team, but in progress. All mapping is complete, following consultations with ADREs, DoGEs, Research and Enterprise (now RIKE), People and Organisational Development. Dissemination actions expected to be completed spring 2022, evaluation in May 2022 and June 2023. |  | Continue
* The Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
KEY
CEDARS | Note that for all scores, 'agree' and 'mostly agree' or 'useful' and 'mostly useful' scores (and equivalents) have been combined.
KEY
ADRE | Associate Deans for Research and Enterprise
CEDARS | Culture, Employment and Development in Academic Research Survey, combining, revising, and replacing CROS and PIRLS from 2020
CROS | Career Researcher On-Line Survey (Biannual) - replaced by CEDARS
Chair AS | Chair of Athena SWAN Panel (now superseded by EDIEC)
Chair URCOG | Chair of University Research Careers Oversight Group
Chair EDIEC | Chair of Equality, Diversity and Inclusivity Enhancement Committee (includes remit for Athena Swan).
CMI | Chartered Management Institute
Deans | Dean of Academic Schools
DoGE | Director of Graduate Education
DoGS | Dean of the Graduate School
DoHR | Director of Human Resources
DoM+C | Director of Marketing and Communications
DoRC | Directors of Research Centres/Institutes
DoRE/DoRIKE | Director of Research and Enterprise/Director of Research, Innovation and Knowledge Exchange
ECR | Early career researcher
EDIEC | Equality, Diversity and Inclusivity Enhancement Committee (includes remit for Athena Swan).
HoCS | Head of Careers Service
HoD | Heads of Academic Departments
HoHR | Head of HR
HoOH | Head of Occupational Health
HP&OD | Head of People and Organisational Development (formerly Head of Staff Development)
HoRE | Head of Researcher Environment
HoSD | Head of Staff Development, now Head of People and Organisational Development
OH | Occupational Health
PI | Principal Investigator
PIRLS | Principal Investigator and Research Leader On-Line Survey (Biannual) - replaced by CEDARS
PGR | Postgraduate researcher (includes Doctoral and Masters by Research)
PaOD | People and Organisational Development
PRF | Principal Research Fellow
PVC (R&E/RIKE) | Pro-Vice Chancellor (Research and Enterprise/Research, Innovation and Knowledge Exchange)
QoWL | Quality of Working Life Survey (University Biannual Survey administered externally)
RA | Research Assistant
RC | Research Committee
RDF | Researcher Development Framework
R&E | Research and Enterprise (now RIKE)
RF | Research Fellow
RIKE | Research, Innovation and Knowledge Exchange (formerly R&E)
SL | Senior Lecturer
SRF | Senior Research Fellow
URCOG | University Research Careers Oversight Group (was University Research Careers and Engagement Oversight Group )